Maternal & Child Health Initiatives through Drinking Water & Sanitation Program

Interim Progress Report

(July 2016 - December 2016)

General Background of the Project

This program has been implemented by Tamakoshi Sewa Samiti (TSS), a non-governmental organization based in Ramechhap district of Nepal. World Neighbours Canada Society and DFATD-Global Affairs Canada have jointly funded to implement this project.

Project Period & Funding Amount

The project period has covered a total of 49 months effective from 1st March 2016 to 31st March, 2020. The total approved budget is CAD 394,004 (Nepalese Rupees 28,762,252).

Purpose of the Program

This project will focus on improving the health of mothers, young children and infants in Nepal by providing year-round access to drinking water and sanitary toilets to targeted communities of Ramechhap District.

Immediate Outcome

The immediate outcome of the program is to increase equitable use of potable drinking water and healthy environments by women, men, girls & boys. For this, the program has aimed to achieve the following two major results.

- It will provide 21 gravity-flow water systems that will deliver clean water year-round to approximately 525 families through public tap stands by the end of the project period.

- It will focus on improving the health and sanitation of approximately 4,200 families by facilitating the provision of sealed, hygienic toilet systems next to their houses by the end of the project period.

Plan of Action

Originally, the following target was planned to implement program, however it has revised according district situation and implementation time-frame. The revised figures are mentioned in the bracket.

|  | Description | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | No. of Drinking Water Systems | 2 (1) | 5 (2) | 5 (2) | 5 (9) | 4 (7) | 21 |
|  | No. of families in Drinking Water | 50 | 125 | 125 | 125 | 100 | 525 |
| 2. | No. of toilet construction/families | 300 (X) | 1,000 (2,100) | 1,000 (2,100) | 1,000 (X) | 900 (X) | 4,200 |

Progress & Achievement (July-December2016)

  - Drinking Water Construction:

Two gravity-fed water systems have been finalized for the 2nd year as planned. A detail is as follows:

|  | Name of Scheme | Location | HH | Population |
| --- | --- | --- | --- | --- |
|  |  |  |  | Female | Male | Total |
| 1. | Bhandaritole DW Scheme | Gagal Bhadaure VDC, Ward # 7 | 32 | 86 | 89 | 175 |
| 2. | Jyamirbote DW Scheme | Khimti VDC, Ward # 8/9 | 25 | 66 | 68 | 134 |
|  |  | Total | 57 | 152 | 157 | 309 |

Each water system has 5 public tap stands that will serve to supply drinking water for the entire beneficiary households.

The technical design, drawing & estimation of both DW systems have been carried out by TSS technical persons after meeting with the beneficiaries and water user committee. This has been verified and certified by Er. Kushum Bhattarai, a certified government civil engineer from Ramechhap Municipality office. Some of the scanned copies are attached herewith in the annex.

The procurement process for the construction of both DW systems has been initiated. By 2nd week of Jan 2017, we will finish the procurement of all required non-local construction materials (such as polythene pipe, tools, fittings, cement etc.) and then we transport all these materials at the scheme site. We expect to complete both the water system by the end of Feb 2017.

The baseline survey will be completed by the end of Jan 2017 in the two scheme sites using the standard questionnaire form.

Map of Ramechhap and DW Construction Scheme sites in the map

  - Toilet Promotion Program :

The Government of Nepal has adopted a National Hygiene and Sanitation Master Plan in 2011. The goal of the Master Plan is to attain universal access to improved sanitation by 2017 for better hygiene, health and environment. To achieve the goal, the milestones are set as follow:

Milestone 1 : Toilet coverage of 60% of the total population by 2012/13

Milestone 2 : Toilet coverage of 80% of the total population by 2014/15

Milestone 3 : Universal toilet coverage by 2016/17

In Ramechhap district, Drinking Water & Sanitation Division Office, a government agency, is responsible to achieve above target through collaboration with various social organizations working in the district. There is also District Water, Sanitation and Hygiene Coordination Committee (DWASHCC) headed by Local Development Officer from government office. Being TSS is also involved on water and sanitation initiatives, it is also the member organization of the DWASHCC.

The DWASHCC has approved our plan to work in the following communities to promote toilet construction program and declare Open Defecation Free (ODF) zones by December 2017.

| S.N. | VDC | Total HH | Usable good condition toilet | Partially damaged toilet | Total usable toilets | Fully damaged toilets | HHs having no toilets | Toilet coverage % | Non- toilet coverage % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | District | 48031 | 21416 | 7581 | 28997 | 9030 | 10,004 | 60.37% | 39.63% |
|  | For TSS |  |  |  |  |  |  |  |  |
| 1. | Manthali Municipality | 5728 | 2570 | 1395 | 3965 | 1501 | 262 | 69.22% | 30.78% |
| 2. | Deurali | 809 | 220 | 2 | 222 | 517 | 70 | 27.44% | 72.56% |
| 3. | Dimipokhari | 758 | 498 | 51 | 549 | 63 | 146 | 72.43% | 27.57% |
| 4. | Hiledevi | 798 | 215 | 193 | 408 | 26 | 364 | 51.13% | 48.87% |
| 5. | Pinkhuri | 585 | 47 | 167 | 214 | 307 | 64 | 36.58% | 63.42% |
|  | Total | 8678 | 3550 | 1808 | 5358 | 2414 | 906 | 61.75% | 38.25% |
| Total target households for TSS | 3,320 |  |  |

Source: District Sanitation Strategic Plan (Revised 2016 June)

There are 2 municipalities and 45 VDCs in Ramechhap. The municipalities were declared in December 2015 where 10 VDCs were merged. TSS aims to support 4,200 families to construct household toilet under the WNCS/DFATD-GAC project. The above data is not confirmed and there is possibility of increment of households not having toilets and/or damaged toilets.

In the first phase, TSS has started to work in 3 Village Development Committees (VDCs) namely Dimipokhari, Hiledevi & Pinkhuri.

The toilet construction progress in Dimipokhari VDC is very good. Out of remaining 385 families (as per out survey data), 257 families have almost completed the toilet construction. However, the progress in Hiledevi VDC is almost nothing. In Pinkhuri VDC, only 15 households have started the toilet construction. Despite our several initiatives, the progress has not moved ahead in Hiledevi VDC. The people are saying that our first priority is to construct our damaged homes, not the toilet.

In Dimipokhari VDC, other one NGO called Nyayik Sansar (whose head office office is based in Kathmandu) is also partnering with TSS in toilet program. This NGO has supported for corrugated sheet for toilet roof and 1 bag of cement for each family. That could be one reason there is good progress in Dimipokhari VDC. But this NGO is not working and supporting in other VDCs.

Last week, there was DWASH-CC meeting in DDC office where we also participated. Each NGO has briefed about the progress of toilet construction status of own area. The progress of toilet construction of many NGOs is not satisfactory. The District Development Officer/Chairman of the DWASH-CC has also expressed the doubt to achieve the government target of ODF zone declaration by the stipulated time. However, we will maintain our efforts to achieve the target. Our first aim is to support families who don't have toilet rather than the declaration of ODF zones.

Other toilet related activities

- Baseline data survey : In the first phase, we have conducted baseline survey of toilet program among 93 households in Dimipokhari VDC. The survey at additional households in 
Dimipokhari is still on-going. Once the survey it is completed, the reported will be tabulated.

- Hygiene & Sanitation Training : The hygiene and sanitation training has been conducted among 10 groups consisting 190 participants.

- Political Updates on State Restructure

In the existing constitution of Nepal, there is the stated that the main structure of the Federal Democratic Republic of Nepal shall be of three levels, namely the Federation, the State and the Local Level. There shall be Village Institutions, Municipalities and District Assemblies under the Local Level. With this provision, the term Village Development Committee (VDC) has been replaced with the Village Institutions. However, the VDC is still prevailing in practice.

The government has formed a Local Level Restructuring Commission (LLRC) as per constitutional requirement of a mechanism to determine the number and borders of Village and Municipal Councils. The LLRC has decided to keep the number of local units (including village & municipal councils) to a maximum of 744 after revising restructuring criteria in the entire nation. Nepal currently has 217 municipalities and 3157 Village Development Committees.

The LLRC has allotted the maximum number for each district and there should a maximum number of 8 in Ramechhap district (including village and municipality). Currently, there are two municipalities and 45 VDCs in Ramechhap. After several rounds of meeting among political parties and civil society organizations in Ramechhap, it has decided the 8 numbers with 2 municipalities and 6 village institutions. For this, many VDCs have been merged on the basis of certain population criteria set by LLRC. Once the number of local level is declared by the government, the VDCs will be replaced by village councils/institutions. In that case, there will be only 8 local level government units, instead of current 47 units.

Proposed political map of Ramechhap

3.	Financial Situation (March-December 2016)

The following is the financial situation (budget vs. expenditure) by the end of December 2016.

|  | Budget Headings | A/C | Exp. upto | Expense | Expense | Total | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Code | previous | this | upto | Budget | Budget |
|  |  |  | month | month | this month | (NRS.) | (NRS.) |
| 1 | Personnel |  |  |  |  |  |  |
| 1.1 | Program Coordinator/Supervisor | A 1.1 | 264,000 | 26,400 | 290,400 | 1,607,376 | 1,316,976 |
| 1.2 | Technical Assistants | A 1.2 | 481,800 | 48,180 | 529,980 | 2,933,461 | 2,403,481 |
| 1.3 | Logistic Organizer | A 1.3 | 110,000 | 11,000 | 121,000 | 669,740 | 548,740 |
| 1.4 | Field Account | A 1.4 | 132,000 | 13,200 | 145,200 | 803,688 | 658,488 |
|  | Sub Total |  | 987,800 | 98,780 | 1,086,580 | 6,014,265 | 4,927,685 |
|  | Local Subcontractors |  |  |  |  |  |  |
| 1.5 | Independent Final Evaluation | A 1.5 | 0 | 0 | 0 | 150,000 | 150,000 |
|  | Sub Total |  | 0 | 0 | 0 | 150,000 | 150,000 |
| 2 | Materials & Construction |  |  |  |  |  |  |
| 2.1 | Drinking water program | A 2.1 | 504,078 | 0 | 504,078 | 10,424,560 | 9,920,482 |
| 2.2 | Latrine program | A 2.2 | 1,989,687 | 16,500 | 2,006,187 | 7,362,166 | 5,355,979 |
|  | Sub Total |  | 2,493,765 | 16,500 | 2,510,265 | 17,786,726 | 15,276,461 |
| 3 | Travel & Monitoring |  |  |  |  |  |  |
| 3.1 | Field Travel by Staff | A 3.1 | 68,960 | 0 | 68,960 | 1,039,398 | 970,438 |
| 3.2 | Supervision, Monitoring & Transportation | A 3.2 | 64,690 | 33,960 | 98,650 | 753,531 | 654,881 |
|  | Sub Total |  | 133,650 | 33,960 | 167,610 | 1,792,929 | 1,625,319 |
| 4 | Trainings |  |  |  |  |  |  |
| 4.1 | O & M Training /Post-Construction Training | A 4.1 | 8,540 | 0 | 8,540 | 244,977 | 236,437 |
| 4.2 | Hygiene & Sanitation Training | A 4.2 | 0 | 29,320 | 29,320 | 452,590 | 423,270 |
| 4.3 | Gender Equality & Development Training | A 4.3 | 94,385 | 0 | 94,385 | 87,000 | -7,385 |
|  | Sub Total |  | 102,925 | 29,320 | 132,245 | 784,567 | 652,322 |
| 5 | Other Direct Costs |  |  |  |  |  |  |
| 5.1 | Baseline Data & Follow-up Data Collection | A 5.1 | 38,400 | 25,400 | 63,800 | 1,062,840 | 999,040 |
| 5.2 | Project Audio-video Documentary (with English Subtitle) | A 5.2 | 0 | 0 | 0 | 175,000 | 175,000 |
| 5.3 | Sharing & Review Meeting with Line Agencies | A 5.3 | 28,295 | 0 | 28,295 | 173,995 | 145,700 |
|  | Sub Total |  | 66,695 | 25,400 | 92,095 | 1,411,836 | 1,319,741 |
| 6 | Administration |  |  |  |  |  |  |
| 6.1 | Office Equipments (Laptop, Camera, Printer) | A 6.1 | 190,442 | 0 | 190,442 | 258,000 | 67,558 |
| 6.2 | Local Administration (2% of total cost) | A 6.2 | 24,959 | 58,625 | 83,584 | 563,966 | 480,382 |
|  | Sub Total |  | 215,401 | 58,625 | 274,026 | 821,966 | 547,940 |
|  | Grand Total |  | 4,000,236 | 262,585 | 4,262,821 | 28,762,290 | 24,499,469 |

Cover Page - Bhandaritole DW Scheme

Cover Page - Jyamirbote DW Scheme

Technical Summary - Bhandaritole DW Scheme

Technical Summary - Jyamirebote DW Scheme

Cost Estimation Summary - Bhandaritole DW Scheme

Cost Estimation Summary - Jyamirbote DW Scheme

Pipeline Layout - Bhandaritole DW Scheme

Pipeline Layout - Jyamirbote DW Scheme

Reservoir Design - Bhandaritole & Jyamirbote DW schemes

Approved Toilet Design

Toilet Construction Photos

Toilet Material Transportation & Delivery to Community

Baseline survey photo

Hygiene & Sanitation Promotion

# Text boxes

Manthali headquarter

(TSS Location)

Khimti VDC

Gagal Bhadaure VDC