Progress Report

GENERAL INFORMATION ABOUT THE PROJECT

| Organization Name: | Neighbors Honduras |
| --- | --- |
| Project Name: | "Improving Childhood Education Opportunities and Youth Economic Inclusion" |
| Project Start Date: | July 01, 2025 |
| Project End Date: | December 31st, 2025 |
| Duration in years: | 6 months |
| Period covered by this Report: | July 01 to December 31st, 2025 |
| Date of signing of the Contract: | July 2025 |
| Amount for which the contract was signed: | WNCS CAN17,826.08 (CAN 7,826.08 balance up to June 2025 plus CAN10,000 new contribution) VH contribution CAN2,374.47 Total project CAN 20,000.00 |
| Date of sending this report and name of the person who completed: | January 15th, 2026 Alain Guevara Osorio – Facilitator Carlos Vijil Moreno- Director |

INFORMATION FROM THE PERSON WHO COMPLETED THE REPORT

| Name: | Alain Guevara Osorio |
| --- | --- |
| Responsibility or position: | Citizen Participation Facilitator |
| Phone: | Cell +(504) 9795-1623 |
| E-mail address: | alain1982osorio@gmail.com |
| Skype Address: | None |

- MAIN ACTIVITIES CARRIED OUT

Table 1.1 Activities Planned and Carried Out

| Planned Activities (according to contract) | Activities Carried Out | % of total project implementation |
| --- | --- | --- |
| Promotion and dissemination of native and creole seeds | - Three 3 days of training on the promotion and dissemination of native seeds were held with producers in the communities of El Chaparral, Potrerillos and Isletas Abajo. Exchanges of experience were carried out in conservation practices, selection and dissemination of native seeds, to learn about different ways in which each farmer adapts their techniques according to soil conditions, climate and local customs. The exchanges made it possible to learn about the wealth of traditional knowledge present in peasant agriculture and to strengthen the capacities of producers in proper seed management. 30 people participated (22 women, 8 men) | 100% |
| Establishment of plots or trials | - Three (3) technical accompaniments to producer families in Isletas Abajo, Las Olivas and La Faja communities, where evaluations were carried out to identify better characteristics in corn and bean crops such as: type of flowering, vigor, height, foliage, ear size, flowering synchronization, presence of pests or diseases, soil moisture and uniformity in growth - A demonstration was made on techniques for measuring height, number of leaves, recording of observations and proper use of field notes in corn cultivation. This activity reinforced the importance of keeping an orderly and systematic control of the plot, which will help to validate in the field and make management adjustments; In addition, crop management practices and improvements in activities such as weed control, fertilization, pest management were validated according to the conditions observed in the plot. These activities are useful for analyzing and identifying strengths and achievements. 36 participants (9 men and 27 women) | 100% |
| Soil conservation practices. | - 3 soil conservation practices were carried out with producers from Las Arandas, Isletas and El Aguacatal communities in the layout of contour lines using a transparent hose; contouring is a technique to prevent erosion, improve water infiltration, and increase soil fertility. Other topics addressed were: Principles of soil and water conservation, importance of contour lines to reduce erosion and improve water distribution, advantages of the transparent hose as an instrument to correctly level the land, planning of plots and critical points of erosion. The participants showed interest in making replicas of this technique that serves to identify areas with a higher risk of erosion and accurately trace the leveling of the curves. 25 participants (5 men and 20 women) | 100% |
| Agroecological Practices to Prepare Inputs | - Three (3) practices on preparing agro-ecological inputs in communities El Copetillo, La Faja and Concepción de María using local resources; Prioritized variables were: importance of soil and organic matter, types of fertilizers and bio-ferments, inputs for natural pest control, economic benefits; agro-ecological inputs are made with low-cost local materials; the activity included a practice on making Biol, a natural burner, liquid foliar fertilizer (rich in nutrients and beneficial micro-organisms) to strengthen development of crops. Participants 50 persons (13 men and 37 women) | 100 |
| Characterization of native and creole seeds | - 3 days of training were held in the characterization of native and creole seeds as a tool for selection, registration and valuation of agricultural heritage in communities Concepción de María, Las Olivas and Quebrada Grande; basic concepts addressed include: types of seeds, local and creole varieties, physical and qualitative properties, importance of recognizing quality and purity characteristics of seeds for planting. A practical demonstration was carried out to characterize seeds by analyzing variables such as size, shape, color, weight, healthy and damaged seeds through visual review. Registration of information for documentation and selection. 35 participants (16 men and 19 women) | 100% |
| Visits for characterization of native and creole seeds | - 20 visits were realized to communities in the municipality of Langue to collect information on the type of local seeds used by the producing families. This activity was fundamental to develop public policy proposal for declaration of seeds as heritage of the municipality of Langue approved by the Municipal Corporation in October 2025. Information was obtained from 65 farmers | 100% |
| Follow-up to Healthy Home projects. | - Nine (9) families from Las Olivas, El Llano and Isletas Arriba communities installed 4 chicken coops, 2 housing floor improvements, 2 latrines and a water storage basin; these activities are carried out by providing small loans from the revolving fund managed by Vecinos Honduras and technical support from the WNCS project - 15 monitoring and follow-up visits were made to families in the communities Isletas Arriba, Isletas Abajo, Concepción de María, Copetillo, Potrerillo, Las Arandas and El Llano regarding proper use and maintenance of the improved stove, operation of the chicken coops and latrines | 100% |
| Monitoring of Strategic Grain Reserves. | - Monitoring grain reserves in communities Las Arandas and Concepción de María Centro, strengthening their knowledge in administration, financial education and internal organization | 100% |
|  |  | 100% |
| Additional activities carried out with budget modification approved by WNCS - Monitoring and technical assistance to 158 producers (136 women and 22 men) organized in 11 Local Agricultural Research Committees (CIAL); participated in trials and exchanges with other CIALs, production and dissemination of the use of native seeds, operation of strategic reserves of grains and seeds, as a means to increase food security and supply basic foodstuffs in times of scarcity or crisis, adoption of agro-ecological production practices and participation in peasant fairs to market surplus production and processed products - Technical assistance and training to 99 producers organized in 6 strategic grain reserves (4 in follow-up and 2 organized in this semester). Two of these reserves obtained small loans from the Vecinos Honduras revolving fund in June 2025 - Follow-up and support on holding community assemblies to restructure boards of directors of health committees in La Faja and Las Olivas communities; 33 women and 16 men participated in assemblies interested in continuing to promote community development focused on health, healthy eating and citizen participation - Participation with leaders of other communities supported by other projects of Vecinos Honduras in the preparation, presentation, advocacy actions and efforts for approval of the public policy of declaring native and creole seeds as heritage of the Municipality of Langue approved by the Municipal Government, which also committed to promote and support the application of the measures contained in the declaration |  |  |

If, as of the date of this report, any activity(s) were not executed as planned, please indicate the reasons for their non-non-compliance

Water chlorination kits were not installed in wells because there was no positive response from the organizations involved

- MONITORING OF PROGRESS OF RESULTS

| Expected Indicators (according to the contract) | Results Achieved to Date |
| --- | --- |
| Specific objective 1: To improve the pedagogical conditions of educational centers in rural communities. |  |
| R.1.1: Improved the infrastructure of three (3) schools in the communities of San Marcos, Isletas Abajo and Potrerillos. | Follow-up in the construction of three (3) rainwater harvesters, installing a 2,500-liter Rotoplas tank on a concrete base, PVC plastic channel for water harvesting, four toilets and the installation of six (6) sinks in communities of San Marcos, Isletas Abajo and Potrerillos Parents pending to take care of the physical works of the educational centers of the communities of Potrerillo, Isletas Abajo and San Marcos Tamayo |
| R.1.2: Installation of six (6) kits for chlorination of wells to improve water quality. | Meetings were held with representatives of six water boards in which the idea of installing kits for water treatment using chlorine was proposed. There was no positive response from the boards of directors arguing that the users of the water services reject the application of chlorine in water because of the change in flavor that this product produces. As a second option, it was proposed to clean drilled wells that have sediments, for which they should contribute with cash contributions by the members of JAA and contributions from the Municipal Mayor's Office; This proposal also did not receive a response from the local government or the organizations that manage the systems, arguing lack of funds. For the reasons explained this activity was not carried out |
| Specific Objective 2: Implementation of agroecological practices and soil conservation |  |
| R.2.1: 20 young people (men and women) complete training program in technical areas to provide various services (electricity, agriculture, and dressmaking) | No activities planned for the semester July to December 2025 |
| R.2.2: Establish a financing fund for income-generating initiatives for young graduates of the training program or other interested parties. | In follow-up visits, it was verified that three young people trained in INFOP have installed and continue to operate electric welding workshops in their communities with their own funds without making use of the financing fund of Vecinos Honduras |
| Specific Objective 3: Strengthening the institutional capacity of Vecinos Honduras for the provision of services |  |
| R.3.1: Salaries of Food Sovereignty Facilitator, Health Facilitator and Administrative Coordinator | Services for specific activities were paid to the Health Facilitator (5 days per month) Salaries for Agro-ecology Facilitator (full-time) serving CIAL groups and strategic grain reserves Administrative Coordinator (percentage of salary) during the period |
| Additional activities carried out with budget modification requested and approved by WNCS There were no changes during the reporting period |  |

Main Problems in the Execution of Activities and Strategies of Approach

1. Migration: Young people (men and women) migrate to urban centers in Honduras, United States and Spain looking for employment opportunities; this causes the withdrawal of participants in project activities

Measures adopted: Promote greater participation of young people in the activities of the projects so that they find alternative lives in various occupations and do not have to migrate

2. Climatic phenomena: There were no problems due to natural phenomena during the reporting period; reported risks are related to isolated rains and short periods of drought that did not affect the development of activities

Measures adopted: During the second half of 2025, efforts were concentrated on supporting producers in capacity building and protection of water and seed resources and adoption of agro-ecological production technologies

3. Electoral campaign: The general elections in November 2025 were held with a lot of uncertainty regarding the possibilities of fraud, violence and polarization among supporters of political parties; fortunately, the electoral process ended peacefully. The situation changed after the elections when the authorities of the National Electoral Council (CNE) showed many deficiencies and little transparency in the presentation of the results at the presidential level, deputies to the National Congress and Municipal Mayors' Offices, which increased tensions and suspicion of fraud that caused unresolved conflicts to date

Measures adopted: As part of the Contingency Plan applied by Vecinos Honduras, it was decided to advance in activities related to health and hygiene at home, agriculture and avoid public events during the week prior to elections to reduce risks to staff and participants in case of violence

- TOTAL NUMBER OF PEOPLE DIRECTLY PARTICIPATING IN THE PROJECT

Please include in the following table all the people who are directly involved in the activities of the Project. Each person must be included only once

3.1 Concepción de María, Language

| Direct participants in activities |  |  |  |  |
| --- | --- | --- | --- | --- |
| Producers organized in CIAL |  |  |  |  |
| Communities | # CIAL | Women | Men | Total producers |
| Isletas Arriba, Las Olivas, El Copetillo, El Llano, La Faja, Potrerillos, El Aguacatal, Las Arandas, Isletas Arriba and Concepción de María Centro | 11 | 136 | 22 | 158 |
| Producers Organized in Strategic Grain Reserves |  |  |  |  |
| Communities | # Grain Reserves | Women | Men | Total, producers |
| Concepción de María Centro, Las Arandas, La Faja, Las Olivas, Quebrada Grande, Apazala | 6 | 69 | 30 | 99 |
| Health Committee |  |  |  |  |
| Communities | Health Committees | Women | Men | Total |
| San Marcos, Potrerillos, Las Arandas, Concepción de María, El Aguacatal, El Copetillo, El llano, Isletas Arriba, La Faja, Isletas Abajo and Las Olivas. | 10 | 62 | 12 | 74 |
| Total direct participants |  | 267 | 64 | 331 |

- ELEMENTS THAT CONTRIBUTED TO THE IMPLEMENTATION OF THE PROJECT

For the project to be executed well, it is evident that there is the contribution of several elements of internal and/or external origin to the executing organization, which it is necessary to identify in order to continue taking advantage of its influences and characteristics. Please identify and assess those aspects that are favoring the execution of the project

| Identified Element | Positive contribution to the Project | Internal or External Origin? |
| --- | --- | --- |
| Community leadership | Community organizations (Water Management Boards, Boards, Health Committees, Parents' Associations, Women's Network) with capacities and greater community leadership participate in all community activities | External |
| Complementarity of actions with other projects of Vecinos Honduras | Resources are complemented and leveraged in logistics (transportation, office use and various services), expansion of impact in activities, population served and comprehensive responses are offered to the needs and potentialities of the communities | Internal |
| Linkage with public actors such as the Ministry of Health, Education and the Municipal Mayor's Office, among others. | It has facilitated coordinated activities on health issues | External |
| Coordination with the Cooperativa de Ahorro y Crédito Esfuerzo Langueño Ltda (CACEL) | Vecinos Honduras is a member of CACEL, which maintains a savings account of the revolving fund for small interest-free loans to families who adopt Casa Hogar Saludable tecnologies. Families make payments to Vecinos Honduras through deposits in Saving and Loan Cooperative CACEL | External |

- PROJECT MONITORING AND EVALUATION

It is very important to know how the Monitoring and Evaluation activities have contributed to the control, correction and evaluation of the actions of the Project. Please provide the requested information, with special emphasis on the contribution you have made to the proper execution of the project.

| Monitoring and Evaluation Activity | Was it made? |  |  | Contribution of the activity to the proper implementation of the Project |
| --- | --- | --- | --- | --- |
|  | YES | NO | Date |  |
| Promotion and Dissemination of Native Seeds. | X |  | July-December 2025 | -Meetings with organized producers. -Awareness days for producer families |
| Establishment of plots or trials. | X |  | July to November 2025. | -Demonstration of agro-ecological practices -Local crop assessments -Exchange of practical knowledge |
| Soil conservation practices. | X |  | July to November 2025. | 3 soil conservation practices were carried out for producers in the communities of Las Arandas, Isletas and El Aguacatal, strengthening knowledge |
| Agroecological practices to prepare inputs. | X |  | November 2025 | Developed 3 Biol production practices and a natural burner, a liquid foliar fertilizer, rich in nutrients and beneficial microorganisms that strengthen crops |
| Seed Characterization | X |  | November 2025 | After 3 days for the characterization of seeds, an activity was given to strengthen capacities on the characterization of native and local seeds in Concepción de María, Las Olivas, Quebrada Grande |
| Visits for characterization of native seeds | X |  | November 2025 | 20 visits to the communities of the municipality of Langue were carried out to collect information on local seeds used by producer families as a basis for declaring native and native seeds as heritage of the Municipality |
| Follow-up to Healthy Home projects. | X |  |  | Nine (9) families from the communities of Las Olivas, El Llano, Isletas Arriba were accompanied in the follow-up of their Healthy Home projects |
| Monitoring of Strategic Grain Reserves. | X |  | July to December 2025 | Follow-up visits and technical support to 6 strategic grain and seed reserves by Agro-ecology Facilitator |

- UPCOMING ACTIVITIES:

Please explain, how will the learning obtained in the first months of project execution be incorporated during the time remaining to conclude it?

7.1 How will learning be integrated into the next phase of the project?

- Follow-up on CHS activities and strengthening health committees

- Coordination with the Ministry of Health in carrying out activities in communities

- Promotion and dissemination of the use of native and creole seeds with new families and communities

- Establishment of plots or trials in agro-ecological production as a demonstration effect to expand impact

- Expand the number of families that adopt soil conservation practices such as: Preparing inputs, native and native seeds, soil conservation, diversification of production

- Follow-up to the declaration of native seeds

  - Main achievements

- During the period July to December 2025, 331 people benefited directly in 10 communities (267 women and 64 men) organized in 11 Local Agricultural Research Committees (CIAL), 6 strategic grain and seed reserves (4 existing and 2 new) and 10 community health committees

- The farmers grouped in CIAL and grain reserves received technical assistance and permanent training in the management of maize and bean research plots and the adoption of agro-ecological production practices (natural burning, liquid organic fertilizer, crop diversification, conservation and protection of native seeds); the accompaniment was given by the Agro-ecology Facilitator assigned to the WNCS project. The community health committees received technical support and training on Healthy Home issues (improvement of housing, health and hygiene practices in the home, installation of improved stoves, garbage management) and facilitate coordination and support links with the existing public health service units in the area; these activities were carried out by the Family and Community Health Facilitator hired for five working days each month under the WNCS project. In the case of families that adopted Healthy Home practices (home improvements, latrines, improved stoves), the technical support was complemented with interest-free microcredits with a revolving fund managed by Vecinos Honduras

- Follow-up to activities of the "Building Resilient Communities" project completed in May 2025 with funding from the International Community Foundation (ICF) in technical assistance, monitoring and training processes in protection and conservation of native seeds and family and community health

- Nine (9) communities in the Concepción de María area improve family and community health conditions with the organization of health committees that monitor families who have adopted Casa Hogar Saludable (Healthy Home Practices), community cleaning campaigns for vector control and information campaigns for vaccination and cytology in alliance with public health centers

- Identification of two (2) varieties of red bean seed in the communities of Concepción de María, Isletas Abajo, Quebrada Grande and El Chaparral

Annex

-Photo Gallery

-Annual Financial Report

-Success Story

-Proposal New Grant