Format for Progress Report

GENERAL INFORMATION ABOUT THE PROJECT:

| Organization Name: | Vecinos Honduras |
| --- | --- |
| Project Name: | "Improving Childhood Education Opportunities and Youth Economic Inclusion" |
| Project Start Date: | July 01, 2024 |
| Project End Date: | Jun 30th, 2025 |
| Duration in years: | 12 months |
| Period covered by this Report: | July 01 to December 31, 2024 |
| Date of signing of the Contract: | July, 2024 |
| Amount for which the contract was signed: | CAD 20,000.00 |
| Date of sending this report and name of the person who completed: | 20 December 2024 Alain Guevara Osorio, Facilitator Carlos Vijil Moreno, Executive Director |

INFORMATION FROM THE PERSON WHO COMPLETED THIS REPORT

| Name: | Alain Guevara Osorio |
| --- | --- |
| Responsibility or position: | Project Coordinator |
| Telephone: | Cell +(504) 9795-1623 |
| E-mail address: | alain1982osorio@gmail.com |
| Skype Address: | None |

- MAIN ACTIVITIES CARRIED OUT:

Table 1.1

| Planned Activities (according to the contract) | Activities Carried Out |  | % of total project implementation |
| --- | --- | --- | --- |
| Interviews with school teachers to learn about conditions and identify needs for improvement | A working meeting was held with five (5) teachers, a health promoter and six (6) members of the Parents' Association (APF) to socialize rainwater harvesting projects, learning about general information on educational and health centers, infrastructure situation, priorities and raising the possibility of providing support to improve storage and hygiene and establishing commitments with organizations to carry out concrete actions |  |  |
| Selection of schools | Established coordination with educational authorities at the municipal level to agree on the plan to improve access to water in educational centers, prioritizing the installation of a rainwater harvesting system in the "Ramón Villeda Morales" center in Isletas Abajo community and "José Trinidad Reyes" center in the Potrerillos community |  |  |
| Prepare the technical design of the improvements to be made | The school principals prepared the budget with the support of construction masters (masons) from the communities, review by the facilitator, delivery of designs and list of necessary materials |  |  |
| Construction of the works. | Two (2) rainwater harvesting systems were built, including the installation of a Rotoplast tank, the installation of a sink, the construction of a concrete base to place the tank and the installation of a PVC channel to capture rainwater in "Ramón Villeda Morales" and "José Trinidad Reyes" educational centers in the Potrerillos and Isletas Abajo communities |  |  |
| Track the status of improvements | Five (5) follow-up visits were made to the construction of two (2) rainwater harvesting projects in the Ramón Villeda Morales and José Trinidad Reyes educational centers in the communities of Potrerillos and Isletas Abajo (rainwater harvesting systems and installation of sinks). These projects benefit 98 girls, 91 boys and twelve (12) teachers |  |  |
| Awareness days: proper use of water and importance of hygiene | This activity is planned to be carried out in the next semester |  |  |
| Follow-up meetings with participants of the training program in partnership with INFOP | Four (4) follow-up visits to 15 young people in the process of technical training at the Vocational Training Institute (INFOP), who were trained in electricity, metal structures who completed the plan and received their respective certificate The training of 15 young people (13 men in the electricity, computer and metal structures modules and two (2) young women in computing and electricity from the communities of Las Olivas, El Aguacatal, El Copetillo, Isletas Abajo, Las Marías, La Faja and Concepción Centro completed the training cycle |  |  |
| Facilitate transportation for participants from their communities to the training center (July to November) | Support was provided to 15 young participants in the INFOP training process, providing 50% of the cost of transportation from Concepción de María, Langue to the training center located in the community of El Cohete, Nacaome, Valle |  |  |
| Adapt and socialize the regulations for the operation of the rural financing fund | Progress was made with the revision and adaptation of the regulations for the operation of the rural financing fund with the participation of the Executive Directorate, Administration and project coordinators |  |  |
| Design of mechanisms for approval to submit applications, analysis, approval, supervision and recovery of funds. | Vecinos Honduras signed an agreement with the Savings and Credit Cooperative Esfuerzo Langueño Limitada for administration of Lps. 500,000.00 to finance income generating initiatives for young people trained by INFOP, women groups and other community groups. The funds will be available in 2025 |  |  |
| Follow-up visits to young beneficiaries of the fund to ensure the correct use of the financing | This activity is planned to be carried out in the next semester |  |  |
| Day of socialization of the Institutional Strategic Plan with all the staff of Vecinos Honduras. | With the participation of VH staff and the accompaniment of a consultant, the Institutional Strategic Plan of Vecinos Honduras (2024-2028) has been prepared and socialized, with a guiding document on the operational and strategic aspects at the institutional level, definition of strategic components |  | 100% |
| Establishment of the sub-headquarters with the basic equipment necessary for its operation. | There is a sub-headquarters in the Concepción de María community to facilitate the operations of the project in the territory, holding sectoral meetings, lodging and storing equipment and materials |  |  |

- MONITORING THE PROGRESS OF THE RESULTS

| Expected Indicators (according to the contract) | Results Achieved to Date |
| --- | --- |
| Specific Objective 1 To improve the pedagogical conditions of educational centers in rural communities |  |
| R.1.1: Improved infrastructure of three (3) schools | Close coordination with teachers and parents of the Ramón Villeda Morales and José Trinidad Reyes educational centers in communities Isletas Abajo and Potrerillos Construction of two (2) rainwater harvesters, installing a 2,500-liter Rotoplas tank on a concrete base, PVC plastic channel for water harvesting and installation of two (2) sinks Improved conditions of access to water to improve hygiene conditions in which students and teachers carry out educational work Parents committed to improving the physical conditions of the educational centers provided the counterpart in labor and transportation of material. |
| Specific Objective 2: Create opportunities for technical training and insertion of young people in income-generating initiatives |  |
| R.2.1: 20 young people (men and women) complete training program in technical areas to provide various services (electricity, agriculture, and dressmaking) | 15 young men (13 men and 2 women) trained in the technical areas of metal structures, computing and electricity, from communities Las Olivas, El Aguacatal, El Copetillo, Isletas Abajo, Las Marías, La Faja and Concepción centro, who have successfully completed their training process, receiving their respective INFOP certificate |
| R.2.2: Establish a financing fund (L27,500.00) for income-generating initiatives for young graduates of the training program or other interested parties. | An agreement has been established between Cooperativa Esfuerzo Langueño Limitada and Vecinos Honduras for the administration of the fund for financing income-generating initiatives and the mechanism for granting financing, approval, disbursements and recovery has been defined Funds will be available in 2025 for young people interested in starting income-generating activities |
| Specific Objective 3: Strengthening the institutional capacity of Vecinos Honduras for the provision of services |  |
| R.3.1: Prepared on Institutional Strategic Plan of Vecinos Honduras (2024-2027). | Developed and socialized the Institutional Strategic Plan of Vecinos Honduras (2024-2028) the guiding document in the operational and strategic development of Vecinos Honduras for the next five years |
| R.3.2: A sub-headquarters of the Southern Regional Office established in the community of Concepción de María, Langue). | Sectoral office established in the upper area of Concepción de María, Langue to facilitate the activities of technical staff |

Main difficulties and strategies for approaching:

Climatological phenomena: The southern zone suffered damage due to excessive rainfall in November, caused by tropical storm "Sara" that caused soil saturation, loss of bean production and destruction of access roads to communities. This will cause a decrease in the bean crops, one of the main sources of income and food for families in the communities where Vecinos Honduras works

Solution measures: Vecinos Honduras suspended field activities in the affected communities for 3 days; however, the coordination and communication maintained with community organizations allowed many activities not to be delayed

- TOTAL NUMBER OF PEOPLE PARTICIPATING IN THE PROJECT

| Community/Group (List only communities where work is being done) | Families in Community | No. People involved in the project |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Men | Women | Young people | Children Girls | Total |
| The Aguacatal | 88 | 15 | 14 | 5 | 7 | 41 |
| Las Arandas | 11 | 4 | 6 | 3 | 4 | 17 |
| Paddock | 47 | 19 | 13 | 7 | 15 | 54 |
| The Copetillo | 34 | 14 | 19 | 4 | 12 | 49 |
| Islets Down | 29 | 9 | 21 | 6 | 9 | 45 |
| Islets Up | 20 | 8 | 12 | 3 | 6 | 29 |
| Las Olivas | 60 | 9 | 17 | 8 | 7 | 41 |
| Total | 289 | 78 | 102 | 36 | 60 | 276 |

- ELEMENTS THAT CONTRIBUTE TO THE EXECUTION OF THE PROJECT

| Identified Element | Positive contribution to the Project | Internal or external origin? |
| --- | --- | --- |
| Community leadership. | Members of the women's network organized in groups of friends in permanent support of project's activities Leaders of parents' associations from schools where improvements were made | External |
| Coordination with institutions present in the municipality. | Municipal District Director of the Ministry of Education in Langue | External |
| Multidisciplinary Technical Team in the area of influence of the project. | Five (5) field technicians accompanying the participating families on agro-ecological production, organizational strengthening, productive initiatives and integrated water management | Internal |
| There are two (2) local offices in the area, one from Langue city and the other from Concepción de María | There are two (2) local offices to facilitate permanence in the communities, shorter trips and with greater security, generating more commitment and better communication with grassroots organizations | Internal |
| Young people in the process of vocational technical training facilitated by INFOP | 15 young people from the communities of Las Olivas, Isletas Arriba, El llano, El Aguacatal and La Faja participate in the technical training process in INFOP, generating skills in computing, electricity, metal structures | Internal |

- FACTORS THAT LIMIT OR HINDER THE EXECUTION OF THE PROJECT

What do you consider to have been the internal and external factor(s) that limit or hinder the achievement of the Results and/or Indicators foreseen in the project?

| Identified Element | Limiting influence on the Project | Internal or external origin? |
| --- | --- | --- |
| Migration | Migration of young people leaving their communities to the United States. Twelve (12) young people who started a technical training plan at INFOP withdrew to travel to USA and only 15 of 27 completed the training plan | External |

- PROJECT MONITORING AND EVALUATION PROCESS:

It is very important to know how the Monitoring and Evaluation activities have contributed to the control, correction and evaluation of the actions of the Project. Please provide the requested information, with special emphasis on the contribution you have made to the smooth running of the project

| Monitoring and Evaluation Activity | Was it made? |  |  | Contribution of the activity to the proper implementation of the Project |
| --- | --- | --- | --- | --- |
|  | YES | NO | Date |  |
| Interviews with school teachers to learn about conditions and identify needs for improvement. | X |  | August 2024 | -Coordination with principals and teachers of educational centers -Socialization meeting of the project with the educational community -Hiring of a master builder for construction |
| Construction of the works. |  |  | October- November 2024. | -Meeting with the Parents' Association (APF). -Purchase and transfer of materials to schools. -Collection of local materials by the community. -Design of the work to be carried out |
| Track the status of improvements |  | x |  | It is planned for the next semester. |
| Awareness days: proper use of water and importance of hygiene |  | x |  | It is planned for the next semester. |
| Follow-up meetings with participants of the training program in partnership with INFOP. | X |  | July-November 2024. | -Accompaniment of young people in formation on a regular basis- -Follow-up visits with the head of INFOP to learn about the performance of the young people. |
| Facilitate transportation for participants from their communities to the training center (July to November) | X |  | July-November 2024. | Payment of 50% of the cost of transportation for mobilization of young people to the training center |
| Follow-up visits to young beneficiaries of the fund to ensure the correct use of the financing |  | x |  | Planned for the next semester |
| Adapt and socialize the regulations for the operation of the rural financing fund | X |  | September-November 2024. | Established the agreement between Cooperativa Esfuerzo Langueño Limitada and Vecinos Honduras for the administration of funds. The regulations for the operation of the rural financing fund with the participation of the staff of Vecinos Honduras have been prepared and socialized |
| Design of mechanisms for approval to submit applications, analysis, approval, supervision and recovery of funds. | X |  | September-November 2024. | The mechanism for approval, disbursements and recovery of funds has been defined. |
| Socialization day of the Institutional Strategic Plan with all the staff of Vecinos Honduras | X |  | August-September 2024. | Socialized and provided feedback on the institutional strategic plan 2024-2028 |
| Installed and operating sub-headquarters office Vecinos Honduras in Concepción de María community | X |  | August-September 2024. | Project technicians carry out field activities based at the sub-headquarters, which facilitates activities and maintains links with community leaders and organizations |

- UPCOMING ACTIVITIES:

Please explain, how will the learning obtained in the first months of project execution be incorporated during the time remaining to conclude it?

7.1 Main useful learnings next project period

To continue supporting the execution of infrastructure projects in schools, close communication with educational authorities, teachers and parents is essential. These actors will continue to be involved in the remainder of the project

Follow-up of young people trained in technical areas by INFOP to promote entrepreneurship and facilitate training in business development, so that they can implement their learning and generate economic income.

Establish synergies with other projects for comprehensive accompaniment, developing the necessary skills to ensure success in productive initiatives.

A key element will be the complementarity between several projects implemented by VH on different issues that are a priority for families, organizations and communities

7.2 Main achievements.

15 young people trained in the technical areas of computing, metal structures and electricity, who have successfully completed their training process, receiving their respective INFOP certificates.

Construction of two (2) rainwater harvesters, installing a 2,500-liter Rotoplas tank on a concrete base, PVC plastic channel for water harvesting and the installation of two (2) sinks), benefiting 98 girls, 91 boys, seven (7) teachers and five (5) teachers

ANNEXES

See photo annex and success stories