Format for Progress Report

GENERAL INFORMATION ABOUT THE PROJECT:

| Organization Name: | Vecios Honduras |
| --- | --- |
| Project Name: | "Social Economy and Citizen Participation |
| Project Start Date: | July 01, 2023 |
| Project End Date: | Jun 30th, 2024 |
| Duration in years: | 12 months |
| Period covered by this Report: | January 01 to June 30, 2024 |
| Date of signing of the Contract: | July, 2023 |
| Amount for which the contract was signed: | CA$ 30,000 |
| Date of sending this report and name of the person who completed: | 31 July 2024 Alain Guevara Osorio and Manuel Castellanos |

INFORMATION FROM THE PERSON WHO COMPLETED THIS REPORT:

| Name: | Alain Guevara Osorio, Social Facilitator Carlos Vijil M, Executive Director |
| --- | --- |
| Responsibility or position: | xxx |
| Telephone: | Cell +(504) 9795-1623 |
| E-mail address: | alain1982osorio@gmail.com |
| Skype Address: | None |

- MAIN ACTIVITIES CARRIED OUT:

Complete the following table, listing the activities specified in the respective contract and the activities that have been effectively executed to date. Please inform about the specific number of each activity performed. (For example, 5 workshops were held in 3 communities and 20 health facilitators attended all three workshops.)

Table 1.1 Planned and Realized Activities

| Planned Activities (according to the contract) | Activities Carried Out |  | % of total project implementation |
| --- | --- | --- | --- |
| At least one monthly advisory and training visit to each group by the Project Coordinator and/or Facilitator in each area | Aabache Zone Five (5) visits were made to CRAC groups in the communities of El Bonetón, Las Flores, Santa Fe and La Libertad, where progress was made with support in advice on the management of funds granted, follow-up on loans to remember the commitments agreed according to their agreements established with VH, in the same way the internal organization was strengthened with the discussion of its internal regulations and the role of each of the members of the Boards of Directors. The members of the CRAC are fulfilling their commitments and maintaining their organization in the different productive activities, including the planting of beans, coffee and corn, as well as the production, packaging and marketing of banana slices. Concepción de María, Choluteca Made 12 visits to eight (8) Strategic Grain Reserves in the communities of Las Trojas, La Majada, La Nueva Unión, Las Mesas, San Isidro, El Peñón #1, El Peñón #2 and La Plomosa for the preparation of an initial diagnosis with the accompaniment of INFOP, encouraging the importance of training on administration and encouraging participation in the organization. Members of the groups committed to participate and improve the productive activities they develop and maintain their organization, allowing them to advance in continuing to develop their skills and capacities. 17 adult men, nine (9) young men, 14 adult women, and 15 young women participated, in total 55 people participated. Made two (2) visits to groups organized in productive initiatives (IP) production of tajaditas and tinsmithing in the communities of Las Trojas and El Peñón #2 to inform the members of the organization about the activities they are carrying out, learn about the operation, process of elaboration of tajaditas and diversification. Nine (9) adult women, three (3) young women, four (4) young men and two (2) adult men participated in the activity, a total of 18 people participated. Concepción de María, Langue Nine (9) accompaniment visits to 11 leaders of the communities (El Aguacatal, El Copetillo, Las Olivas, La Faja, Isletas Abajo, Isletas Arriba, Las Arandas, Potrerillo and El Llano), to plan activities, socialize the objective of the project and follow up on community organizations (Patronatos, Juntas Administradoras de Agua and CIAL). |  | 100% 100% |
| 2 social economy workshops of two days each (one in Concepción María Choluteca and one in Langue) 15 participants each workshop | Two (2) training workshops (38 women, 1 man and 8 young people, total 47 people) on business management and basic accounting with members of productive initiative groups in communities (Las Olivas, La Faja and Isletas Abajo), to strengthen capacities in the management of their productive initiative |  | 100% |
| Training sessions at the service of social economy groups and reserves for the use and up-to-date management of books and accounting and administrative information record formats | One (1) training module # 2 on the day for directors of organized groups from the communities of La Plomosa, La Majada, Las Trojas, El Peñón #2 and El Peñón #1 on topics of purchase and sale of products, records and sales expenses. The six (6) monthly plans of each group were reviewed, identifying meetings, purchases and other complementary activities, reinforcement in the updating of the accounting record books of inputs and outputs; The groups are replicating the knowledge acquired. Five (5) young women, seven (7) adult women, four (4) young men, six (6) adult men a total of 22 people participated. One (1) sectoral meeting was held with seven (7) leaders of groups that manage strategic grain and seed reserves (RE) of the municipal women's network to learn about their activities, who are updating their daily records, have a board of directors, have monthly contributions and savings; they make loans to members and individuals in a range of 8% to 12% interest; Each grain reserve has diversification of activities such as consumer stores, food marketing and has its own funds. Three (3) young women, one (1) adult man and 10 adult women participated, in total 14 people participated. Five (5) training sessions were held with the support of local volunteers in the communities of La Plomosa, Las Trojas, Las Mesas and Nueva Unión in the II module aimed at directors of organized groups of strategic grain and seed reserves on issues related to administration (records of purchase, sale of inputs, grains and materials, etc.). sales plan and profits. 21 adult women, seven (7) young women, six (6) young men, seven (7) adult men, in total 41 people were the participants |  | 100% |
| Provide 10 financing projects to social economy groups and strategic reserves in Concepción María Choluteca and Concepción de María Langue. | Azabache In this period, Yesica Lizet Lagos received financing of L. 15,000.00 on 09/01/2023 for the strengthening of the family enterprise for the production, processing, transformation and marketing of banana slices, the loan expires on 09/06/2024 (12 months). A loan of L. 300,000.00 was approved for a term of 12 months at an annual interest rate of 12% to the Caja Rural El Progreso of the Las Flores #2 community, the organization is made up of nine (9) men and seven (7) women, in total there are 16 people A loan of L. 20,000.00 for a term of 12 months at an annual interest rate of 12% was approved to the Caja Rural Nuevo Porvenir of the Buena Esperanza community, the organization is made up of 19 men and 13 women, a total of 32 people A loan of L. 56,500.00 was approved for a term of 12 months at an annual interest rate of 12% to the group Young Fighters of the community of Santa Fe, the organization is made up of six (6) men two (2) women, in total eight (8) people. A credit to Ever Perez of L30000.00 was approved A total of L504,000.00 on credits given in 2023 were payed to VH during this semester Table #1. Summary of loan payments #; Group; Loan Lps; VH Interest. L.. CRAC Progress; 130,000.00; 33,000.00. CRAC Porvenir; 114,000.00; 7,980.00. CRAC Vision to Thrive; 35,000.00; 2,800.00. Young Fighters Group; 55,000.00; 2,080.00. CRAC New Generation; 130.000.00; 14,000.00. Ever Pérez; 25,000.00; 2,080.00. Yesica Lagos; 15,000.00; 1,350.00. Total.; 504,000.00; 63,290.00. Table #2 Summary of new loans #; Group; Loan L; % Interest Rate. CRAC El Progreso; 300,000.00; 12. CRAC Porvenir; 20,000.00; 12. Young Fighters Group; 56,500.00; 012. Ever Pérez; 30,000.00; 12. Total.; 406,500.00; 12. Concepción de María, Langue In Concepción de María Langue, financing for social economy groups hasn´t been approved, however, the potential and possibility of supporting them in the future has been identified to a Women's Network, with 130 women from 8 communities that manage Strategic Grain Reserves; in the coming months will be defined the work with these groups |  | 100% |
| Sponsor the participation of at least 30 group leaders in events (fairs, meetings, expo-fairs) | The regional meeting of organized producers was held, with the participation of producers from the communities of the municipality of Langue, Nacaome, Pespire and Concepción de María, department of Choluteca, with the municipality of Langue being the place of the meeting, achieving the exchange of organizational and productive experiences, strategies and methodologies implemented by the organizations, knowing the coordinated work of the different institutions, sharing the achievements made in the year as well as difficulties. An expo was held for the sale of local products, where participants compared fresh agro-ecological products. 65 women and 88 men participated in the activity, a total of 153 people participated. The project financed the mobilization of 23 participants from the area of Concepción de María, Choluteca. Concepción de María, Langue Vecinos Honduras launched the projects in the southern zone, the event was attended by representatives of the participant families and organizations of all projects, authorities and local and regional institutions (Municipal Mayor's Office, ADEPES, AHJASA, Cooperativa Esfuerzo Langueño Limitada, Ministry of Public Health, Ministry of Education, INFOP, Honduran Red Cross) Thirty (30) producers (men and women) sold products harvested in their orchards and plots in this event |  | 100% 100% |
| One water supply system repair and maintenance workshop (2 days15 people) in Concepción de María, Langue | Concepción de María, Langue Two (2) training workshops on the repair and maintenance of water supply systems in the community of Isletas Abajo and Langue Centro, with the participation of managers and plumbers from the communities (Apazala, El Aguacatal, El Chaparral, Agua Zarca, El Mogote, Concepción de María Centro, Las Olivas, Desvío El Tránsito, La Faja, Las Marías and San Marcos), to strengthen capacities in the administration and maintenance of community water systems. Participants: 35 men, 9 women and 3 young people, a total of 47 people |  | 100% |
| One workshop (one day with 10 participants) on the use of the chlorination system, sources of supply in Concepción de María, Langue | A training workshop on rational use of water and proper sanitary inspection with members of Water Administrative Boards and plumbers from the communities (Agua Zarca, Apazala, El Mogote, Concepción de María, El Chaparral and El Aguacatal), to strengthen capacities in the sustainable management and conservation of water systems. Participants: 17 people (10 men, 1 woman and 6 young) |  | 100% |
| Two workshops (one in Concepción de María Choluteca and another in Langue, two days each workshop with 15 participants) at DESCA | A training workshop on Economic, Social and Cultural Rights (ESCER) was held with the Water Management Boards (JAA) and Committees for the Defense of Nature (CDN), who learned about Economic, Social and Cultural Rights (ESCER), appropriating basic conceptualization, the importance of recognition and promotion for the defense of their local resources. The participants with the greatest awareness of taking advantage of the learning spaces on these issues relevant to their organization and communities, being that there are threats of exploitation of resources in the area. Five (5) women and eight (8) men participated, in total there were 13 people who participated. Concepción de María, Langue An exchange of experience between producers with the accompaniment of the Association of Ecological Committees of Southern Honduras (ACESH) in the celebration of World Earth Day, focusing on participation in the defense and protection of natural resources, specifically in conservation of seeds in the municipality of Concepción de María, Choluteca. 59 members of community organizations from San Marcos, Quebrada Grande, Apazala, El Chaparral, Isletas, Concepción de María Centro, Las Olivas and La Faja participated |  | 100% 100% |
| Prepare 8 PACs in a participatory manner for the same number of community organizations in Concepción de María, Langue | Eight (8) community action plans were developed in the communities (El Aguacatal, Isletas Abajo, El Mogote, Agua Zarca, Las Olivas, El Chaparral, El Copetillo and Concepción de María center), to identify problems and needs in their community, identify alternative solutions in the short, medium and long term; participants: 89 women and 20 men, a total of 109 people |  | 100% |
| Two educational tours (one with JAA and one with CDN de Langue) with 10 participants and one day each | A working meeting with members of the JAA to share some progress of cleaning activities in the community and the preparation of the soil for crops A meeting with teachers from the school in the community of El Chaparral, to talk about the establishment of a community nursery with the participation of students and community organizations and the installation of a tank to store water in the school building. The community will provide the labor and the budget was prepared with all the attendees. Participants: 6 men and 2 women, total 8 people |  | 100% |
| Install a water tank to collect rainwater in a school building with the participation of leaders and members of local organizations in Concepción de María, Langue. | Concepción de María, Langue A rainwater harvesting tank for storage water was carried out at the "Juan Lindo" Basic Education Center in the community of El Chaparral, with the involvement of community organizations (Board of Trustees, School Government, teachers and Parents' Association). The facility has rainwater harvesting through the installation of a Rotoplas tank, installation of sinks and conditioning of the existing bathrooms (improvement of the floor with ceramics, installation of 2 toilets, construction of two (2) wooden doors). Total benefits: 74 girls, 52 boys and 8 teachers |  | 100% |
| Submit a proposal to the Municipal Corporation of Langue for the declaration of native seeds as heritage of the municipality. | Plans are to begin next year with the promotion, organization and execution of actions for the declaration of native seeds as local heritage of the municipality of Langue, Valle. In this sense, an event has been developed to publicize the process of agro-ecological work with producers organized in CIAL, strategic grain reserves, achieving exchanges of products, seeds and didactic material to disseminate learning in the field. Concepción de María, Langue 59 members of community organizations and producers from San Marcos, Quebrada Grande, Apazala, El Chaparral, Isletas, Concepción centro, Las Olivas and La Faja participated in a meeting to analyze challenges of producers in agro-ecological production, environment and conservation of native seeds. Additionaly, they talked about experience in the defense, protection and conservation of native seeds and analyze viability to prepare and approval of public policy regarding conservation of local seeds in the Municipality of Langue |  | 100% |
| Community meeting to socialize the WNCS project in Concepción de María, Langue (one day). | A sectoral meeting was held in the community of Las Isletas Abajo with the participation of representatives of the communities of Las Olivas, Isletas Abajo, Isletas Arriba, El Copetillo, El Llano, El Aguacatal and Las Arandas); the work to be carried out in the area was socialized Concepción de María, Langue Vecinos Honduras launched the projects in the southern region in an event where they shared with the participants of all the projects, local and regional authorities (Municipal Mayor's Office, ADEPES, AHJASA, Cooperativa Esfuerzo Langueño Limitada, Ministry of Public Health, Ministry of Education, INFOP, Honduran Red Cross), to inform about the objectives, outcomes and activities of the projects |  | 100% |

If, as of the date of this report, any activity(s) were not executed as planned, please indicate the reasons for their non-non-compliance

Table 1.2: Other activities carried out outside the contract (if any)

| Activities Carried Out | Quantity | Place |
| --- | --- | --- |
| - A zonal forum was held to monitor the municipal policy on native seeds with the participation of producers, municipal corporations, representatives of local institutions and organizations on 08/18/23 in Concepción de María, Choluteca, focused on the issue of care, conservation and protection of local native seeds, their importance in healthy eating and advances in advocacy to value the material that communities have (varieties of beans, corn and maicillo seeds and vegetative material (cassava and sweet potato). The socialization of public policy was carried out, explaining the lines of action and strategies for producers to defend their assets while decision-makers comply with the implementation of their commitments in an articulated manner with the organizations and institutions present in the municipality. 31 women and 29 men participated, in total there were 60 people participating in the event. - With financial support from the Lutheran World Federation (LWF), the construction of two (2) seed collection centers (corn and beans) was completed in the communities of Las Trojas and El Peñón #2. - The ERW supplied 500 pounds of native bean seed and 160 pounds of native corn seed selected with quality standards by the producers organized in CIAL for the planting of collective plots in the spring and late production cycles to producing families in the communities of Las Trojas, San Isidro, El Peñón #2, La Plomosa, Nueva Unión and El Peñón #1. - Construction of three (3) solar dryers with a drying capacity of 40 quintals each in the communities of El Peñón #2, La Majada and Las Trojas, directly benefiting 22 families organized in CIAL and 109 families indirectly, avoiding post-harvest losses of grains and seeds due to excess humidity, mainly when there are intermittent rains that do not allow the drying work. - With financial support from VH's central office, a training day was held with VH personnel. Progress was made in establishing the foundations on the issue of gender equity, strengthening capacities, clarifying new conceptions of gender, statistical data in Honduras, analysis of the gender strategy focused on the lines of action to be implemented. A support committee was organized to follow up on the implementation of the strategy, and an action plan was developed that is consistent with the institutional strategic plan to be updated. Eight (8) women and six men (6) participated, in total 13 VH staff members participated - Two (2) days were held for the socialization and implementation of the Institutional Gender Strategy in the community of El Transito and Concepción de María, Choluteca, with leaders of different community organizations; With this activity, the capacities of the project participants were strengthened in gender conceptualization, analysis of the prioritized lines of action and the strategies proposed; The participants had a significant participation by making their points of view known, recognizing that women are subjects of rights and that it is necessary to reduce the gaps of inequality and exclusion, strengthening the capacities of the members of their families. 13 adult men, two (2) young men, nine (9) adult women, six (6) young women, in total there were 30 participants, participated in the activity. - A meeting of producers (23/11/2023) was held with the participation of members of community organizations, civil society, representatives of public institutions and local government of the municipality of Langue. This event was a space to publicize the achievements and results obtained, learnings and experiences lived with testimonies of producers, who made known the practices they implement to fulfill their commitment to replicate knowledge, narrate life stories, diversification of their production, improvement in production yields and food diet, availability of seeds and grains, participation of children and women, being a space for learning and exchange; In addition, at the meeting, they marketed products from their gardens, formulated requests from the communities for greater commitment and closeness of the local government to meet their demands. 64 women and 57 men participated, a total of 121 people participated in the event. - 45 families from seven (7) communities of influence of the project have increased yields in corn and bean production by improving local seed varieties and diversifying crop production (cassava, sweet potato, beans, corn, bananas and squash), implementing agroecological practices (bio-fermented, fungicides, foliars and green manures), taking advantage of local resources for healthy production in harmony with nature - 105 producers from the communities of La Majada, El Peñón #2, La Plomosa, Las Trojas, El Peñón #1, San Isidro, Las Mesas and Nueva Unión organized into seven (7) Local Agricultural Research Committees (CIAL) and strategic grain reserves, continue to advance in knowledge and adoption of practices and technology for the production and storage of native seeds. soil preparation with green manures and organic matter for the planting of corn and beans, tracing in contour lines, planting techniques, seed breading, visual analysis of the soils, construction of solar dryers and metal silos for the care and good management of grain and seeds and reduce post-harvest losses - Training of five (5) volunteer facilitators and two (2) community facilitators to support participating families in agro-ecological production techniques, climate change and income generation, being very supportive in the execution of activities and as a strategy to advance with the proposed results and objectives. The capacity building of local producers will contribute to the sustainability of the project's actions when Vecinos Honduras is in the exit phase of the Concepción de María area - The public policy for the protection and conservation of local seeds was socialized with representatives of community organizations of producers (CDN, CIAL and REG), institutions present in the municipality and municipal corporation, making known the strategic lines of action, the legal framework where the policy is based, commitments of those involved, emphasizing the relevance of having a policy that governs the issue of seeds as the basis for rescue, conservation and its use and that communities have healthy food as a human right, being key the permanent demand, vigilance and promotion of local seed guardian organizations to generate awareness and avoid the use of transgenic varieties. Members of the corporation ratified the commitment to support production and to continue allocating resources to the organizations, recognizing the effort that has been made and promoting greater coordination between the institutions that support these initiatives Concepción de María, Langue - Two (2) trainings on the development of rapid assessments, formulation and evaluation of community action plans in Isletas Abajo and Langue Centro with the participation of 16 men and 24 women from the communities of Apazala, Chaparral, Copetillo, Isletas, El Aguacatal, Concepción de Maria Centro, El Trapiche, El Sobrón, El Mogote, El Rincón, Las Marías, Los Llanos, Terrero Blanco. Capacities were strengthened in organizational identity, community action planning, they learned basic concepts about Mission, Vision, strategic planning, diagnosis and preparation of maps as a mean to identify community needs - Support in carrying out a water study to identify the conditions of water sources and analyze alternative solutions in the communities of San Marcos, La Faja, Quebrada Grande, Concepción de María, El Aguacatal, El Copetillo, Las Arandas, Potrerillo, Apazala and Agua Zarca, community organizations participated (JAA of 19 communities) - Water sampling from five (5) water sources in communities El Aguacatal, El Chaparral, Agua Zarca, Las María and El Sobrón for water quality analysis by the Ministry of Natural Resources and Environment (SERNA) - Eight (8) training sessions on the preparation of Community Action Plan in communities El Aguacatal, Isletas Abajo, El Mogote, Agua Zarca, Las Olivas and El Chaparral, El Copetillo and Concepción de María center. Total participants: 109 people (89 women and 20 men) |  | Concepción de María Concepción de María, Choluteca 100% Concepción de María Area, Langue |

- MONITORING THE PROGRESS OF INDICATORS

| Expected Indicators (according to the contract) | Indicators Achieved to Date |
| --- | --- |
| Specific Objective 1 Increase the administrative and financial capacity of social economy groups to be more efficient in providing services in their communities |  |
| Indicator 1 Improvement of the administrative and efficient financial management capacities of their companies in 14 social economy groups (10 in Concepción de María, Choluteca and 4 in Concepción de María; Langue). | In Concepción de María, Choluteca, 10 organized groups are supported; six (6) have advanced in capacity building for the sustainability of their initiatives of strategic grain reserves, tinsmithing and transformation of local products in communities of Las Trojas, La Majada, La Plomosa, El Peñón #2; they keep up-to-date accounting records, hold periodic meetings and in permanent productive activity and strengthen the family economy. In the communities of Las Olivas, La Faja and Isletas Abajo in the area of Concepción de María, Langue has been accompanied in strengthening capacities on management, and basic accounting to 22 members of three (3) strategic grain reserves members |
| Indicator 2 It facilitated at least 20 loans to social economy groups and grain and seed reserves in a timely manner and on soft terms. | Financing was granted to Yesica Lizet Lagos' family initiative in the amount of L. 15,000.00 on 09/01/2023 to strengthen the production, processing and marketing of banana slices; The loan matures on 06/09/2024. In Concepción de María Langue, financing for social economy groups hasn’t been approved, however, the potential and possibility of supporting them in the future has been identified to a Women's Network, with 130 organized women from 8 communities that work with Strategic Grain Reserves. In the coming months, the work with them will be defined |
| Indicator 3 Producers and members of social economy groups learn about the experiences and knowledge of similar organizations in the southern region | Two (2) meetings were held between producers organized in the area of Nacaome-Langue and Concepción de María, Choluteca, achieving the exchange of organizational and productive experiences, strategies and methodologies implemented by the organizations, learning about the coordinated work of the different institutions, sharing the achievements made during the year in agroecological production and organizational consolidation, as well as difficulties, mainly due to the effects of climate change. An expo was held for the sale of local products, where participants compared fresh agroecological products. 129 women and 145 men participated in the activity, a total of 274 people participated. Exchange of experience between producers with the accompaniment of the Association of Ecological Committees of Southern Honduras (ACESH) in the celebration of Earth Day, focusing on participation in defense and protection of natural resources, specifically in conservation of seeds in the municipality of Concepción de María, Choluteca. Participants: 59 members of community organizations from San Marcos, Quebrada Grande, Apazala, El Chaparral, Isletas, Concepción centro, Las Olivas and La Faja |
| Specific Objective 2 Enhance the leadership, governance and local development management capacity of community-based organizations |  |
| Indicator 4. 20 JAA managers trained in repair, maintenance, and chlorination of water supply systems. | Four (4) water boards from the communities of Las Trojas, San Isidro, Nueva Unión and El Peñón #1 of Concepción de María, Choluteca, have knowledge about the maintenance and repair of their water supply systems, giving the proper management to the system so that families have a quality service. 47 board members and plumbers from 14 Water Management Boards of 12 communities (Apazala, El Aguacatal, El Chaparral, Agua Zarca, El Mogote, Concepción de María Centro, Las Olivas, Desvío El Tránsito, La Faja, Las Marías, Reducción and San Marcos) trained in the repair and maintenance of water supply systems |
| Indicator 5 30 community leaders are familiar with ESCERs. | 13 leaders were trained on Economic, Social and Cultural Rights (ESCER) with the Water Administrative Boards (JAA) and Committees for the Defense of Nature (CDN) in basic concepts and the importance of knowing and promoting the defense of their local resources |
| Indicator 6 8 grassroots organizations have the PAC as a guiding framework for the development of their activities | Eight (8) community action plans were developed in communities El Aguacatal, Isletas Abajo, El Mogote, Agua Zarca, Las Olivas, El Chaparral, El Copetillo and Concepción de María center, to identify problems and needs in their community, identify alternative solutions in the short, medium and long term, participants: 89 women and 20 men. Total: 109 people |
| Indicator 7 20 community leaders know experiences of similar organizations. | 59 leaders of the communities (Las Olivas, El Aguacatal, Isletas Arriba, Isletas Abajo, El Copetillo, Concepción centro, Las Arandas, San Marcos, Apazala, El Chaparral and Quebrada Grande), shared experiences in the process of agro-ecological production and the declaration of native seeds developed in the communities of Concepción de María, Choluteca |
| Indicator 8 At least 40 leaders increase their capacities in the design and implementation of small local development projects | 33 leaders participated in the training process on project design, management and implementation 15 young people (2 women and 13 men) from the communities of Las Olivas, Isletas Arriba, El Llano, El Aguacatal and La Faja participated in a technical training program in alliance with INFOP dealing with computing, electricity, metal structures, tailoring and beauty; 29 young people (21 young men and 8 young women) started in the program; six (6) young women and eight (8) young men withdrew, these 14 young people withdrew because they migrated to the USA and others did not adapt to the regulations of the training center, they attend the training process twice a month |
| Indicator 9 Municipal Corporation issues resolution declaring native seeds as heritage of the municipality. | An agreement is in progress with the Municipal Mayor's Office for the socialization of work plans related to the process of approval of the Declaration of Local Seeds as Heritage of the municipality |

Main difficulties and strategies for approaching:

Azabache Zone.

Communication with VH headquarters: The internet and telephone signal in Azabache, to communicate with VH central office personnel. The person who monitors the activities travels to Tegucigalpa to deliver plans and reports

Solution measures

Delivery of the report at VH headquarters personally by Manuel Castellanos, responsible for monitoring in the Azabache area

Concepción de María, Choluteca

Increased insecurity in the area of influence of the project, although less frequently criminal acts continue to occur against people, especially merchants

Solution measure: The security plan continues to be applied, putting into practice the protocol to protect the physical integrity of the technical team and avoid unpleasant situations or events to be regretted.

Weather phenomena: The prolonged drought that affected crops during the first half of the year and reduced crop availability

Solution measures: Local organizations maintain strategic reserves of grains and seeds, to supply families in times of scarcity based on the implementation of their marketing regulations and maintain the quality of the products.

Concepción de María, Langue, Valle

Climatological phenomena: The southern region received excess rainfall in June and this caused soil saturation; streams and rivers increased their flow to such an extent that several communities participating in the project were cut off and the staff of Vecinos Honduras faced problems to access the communities to carry out activities; some roads were damaged and it was difficult to mobilize

Solution measures: Vecinos Honduras suspended activities in the affected communities for three (3) days; however, the coordination and communication maintained with community organizations allowed many activities not to be delayed

- TOTAL NUMBER OF PEOPLE WHO ARE PARTICIPATING IN THE PROJECT

Please include in the following table all the people who are directly involved in the activities of the Project. Each person must be included only once

3.1 Conception of Mary

| Community/Group (List only communities where work is being done) | Families in Community | No. People involved in the project |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Men | Women | Young people | Children Girls | Total |
| Las Trojas | 33 | 6 | 9 | 11 | 12 | 38 |
| New Union | 69 | 8 | 12 | 12 | 23 | 55 |
| La Majada | 48 | 5 | 10 | 7 | 14 | 36 |
| The Rock # 1 | 53 | 16 | 11 | 10 | 19 | 56 |
| El Peñón # 2 | 39 | 19 | 14 | 15 | 21 | 69 |
| Total | 242 | 54 | 56 | 55 | 89 | 254 |

3.2: Azabache

| Community/Group (List only communities where work is being done) | No. of Families Community | No. People involved in the project |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Men | Women | Young people | Children Girls | Total |
| La Libertad (CRAC) | 30 | 17 | 11 | 7 | 41 | 76 |
| Santa Fe (Young Fighters) | 14 | 1 | 11 | 9 | 21 | 42 |
| Bonetón (CRAC) | 16 | 13 | 9 | 4 | 52 | 78 |
| Good Hope (CRAC) | 17 | 17 | 2 | 0 | 50 | 69 |
| El Progreso (CRAC) | 21 | 12 | 7 | 22 | 21 | 62 |
| Yesica Lagos | 1 | 3 | 3 | 2 | 3 | 11 |
| Ever Gustavo Pérez | 2 | 2 | 2 | 2 | 2 | 8 |
| Total 2024 | 101 | 65 | 45 | 46 | 190 | 346 |

3.3 Concepción de María, Langue

| Community/Group (List only communities where work is being done) | Families in Community | No. People involved in the project |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Men | Women | Young people | Children Girls | Total |
| The Aguacatal | 88 | 18 | 17 | 4 | 10 | 49 |
| The plain | 51 | 10 | 8 | 3 | 7 | 28 |
| Las Arandas | 11 | 4 | 6 | 3 | 4 | 17 |
| Paddock | 47 | 19 | 13 | 7 | 15 | 54 |
| The Copetillo | 34 | 14 | 20 | 4 | 12 | 50 |
| Islets Down | 29 | 9 | 21 | 6 | 9 | 45 |
| Islets Up | 20 | 8 | 12 | 3 | 6 | 29 |
| Las Olivas | 60 | 17 | 25 | 8 | 7 | 57 |
| The Girdle | 48 | 13 | 19 | 9 | 11 | 52 |
| Total | 388 | 112 | 141 | 47 | 81 | 381 |

- ELEMENTS THAT ARE CONTRIBUTING TO THE EXECUTION OF THE PROJECT:

For the project to be executed well, it is evident that there is the contribution of several elements of internal and/or external origin to the executing organization, which it is necessary to identify in order to continue taking advantage of its influences and characteristics. Please identify and assess those aspects that are favoring the execution of the project

- In Azabache

| Identified Element | Positive contribution to the Project | Internal or External Origin? |
| --- | --- | --- |
| VH work previously carried out, in training processes on transparency issues Provide a fund for capitalization. Appropriation by the partners of the purposes of the organization, internal regulations of each group Management of written loan agreements between groups and partners and VH Tracking of plots cultivated by loan recipients by directors of the groups and V H for payment compliance Inter-institutional coordination Follow-up by VH with personnel in the area of influence | Existence of the different groups in the process of legal constitution, plus the training provided, in organizational, administrative, Financing is provided to social economy groups and entrepreneurs with support from Groundswell International people need it and without interest The groups apply interest of 2% for each loan to capitalize the groups Funding continues to be available for groups and individual enterprises for as long as the beneficiaries need it; this motivates group members because it allows them to capitalize and strengthen their loan portfolio for the non-payment of interest to VH The groups maintain unity and have been increasing their membership, as well as in the management of administrative controls, minute books, savings, contributions, holding planned periodic meetings, managing projects on their own. According to the monitoring carried out, it was verified that social economy groups have made progress in keeping records in the accounting books; This allows for the strengthening of groups, increases trust among partners and allows project activities to run smoothly It is evident that most groups have achieved greater appropriation of their work and sense of relevance, achieving unity and sustainability in their actions The beneficiaries have appropriated the documentation that VH uses to grant revolving fund financing, which allows them to make decisions with ease. In order to ensure the return of the loan, agreements are established between the organized groups and VH, in this way the procedure is more formalized and there are commitments from both parties It allows to ensure the harvest for the payment of the loans by each partner and to VH, it also allows to verify that the crops are growing normally without being affected by pests and diseases In the ordinary and extraordinary meetings held by the groups, the growth obtained in the crops is analyzed, with which the directors and partners ensure that they make the loan payment on the agreed dates, ensure their food and other family expenses such as education, housing, purchase of small plots to expand and diversify their crops. With this, the beneficiaries value the work done by VH and the activities are carried out in the planned time Coordination with the Southern Regional of INFOP to support the strengthening of administrative capacities of members of organized groups in the area of Nacaome, Valle and Concepción de María, Choluteca. The groups are facilitated with better communication with VH, to develop the planned activities in each community. Follow-up and monitoring by the personnel assigned by V H in the area of influence is facilitated. Head office staff including Executive Directorate, Administrative Coordinator, Financial Coordinator and Project Coordinator Groundswell International have provided ongoing support to technical field staff responsible for carrying out activities; in addition, timely vehicle support to monitor on the ground and transport materials when necessary. | Internal Internal I Internal Internal Internal External Internal Internal Internal External Internal |

2) In Concepción de María

| Identified Element | Positive contribution to the Project | Internal or External Origin? |
| --- | --- | --- |
| Community volunteering | There is a commitment on the part of the volunteers that is reflected in the permanent accompaniment of the project's actions. Community leadership committed to the actions of the project, with a sense of belonging and in constant monitoring of the development processes. Leading members of the organized groups leading the activities, fulfilling the commitments and keeping the initiatives running. Team of six (4) facilitators and two (2) facilitators in the process of training, supporting producers in their communities in agro-ecological production and self-employment. | External |
| Coordination with institutions present in the municipality | Good coordination and communication with the Ministry of Health, Education, local government and with the Association of Ecological Committees of Southern Honduras (ACESH). Close coordination with ACESH in the development of public policy on the rescue and conservation of native seeds in the municipality of Concepción de María. Permanent communication with the local government in the realization of actions in the territory and coordination of activities in the spaces we share. | External |
| Incorporation of a specialist technician in the CIAL methodology. | Incorporated into a technician specialized in the CIAL methodology to enhance the agricultural experiment from peasant experiences Seven (7) CIAL organized and functioning, developing agroecological practices, encouraging agricultural experimentation, conservation and use of native seeds in the communities of influence of the project. | Internal |
| Follow-up of organized groups in productive initiatives and strategic grain reserves | 12 groups organized in strategic grain reserves, two (2) productive initiatives for the production of banana slices and tinsmithing were advised on internal organization and basic accounting records. | Internal |

3. Concepción de María, Langue.

| Identified Element | Positive contribution to the Project | Internal or External Origin? |
| --- | --- | --- |
| Community Leadership | Members of the women's network organized in circles in permanent support of the project's activities Community leadership committed to project activities, a sense of belonging and in constant monitoring of the development processes Leading members of the organized groups leading the activities, fulfill the commitments | Internal |
| Coordination with institutions present in the municipality. | Coordination with the Ministry of Health, Education, AHJASA, local government and INFOP Coordination with complementary projects HEKS-EPER, MISEREOR and Groundswell International. Permanent communication with the local government in carrying out actions in the territory and coordination of activities in the spaces we share | External |
| Multidisciplinary technical team in the project's area of influence | Five (5) field technicians accompanying the participating families on issues related to agro-ecological production, organizational strengthening, productive initiatives and integrated water management Nine (9) CIALs organized and functioning, developing agro-ecological practices, encouraging agricultural experiments, conservation of soil, water and native seeds. | Internal |
| There are two (2) local offices in the area, one in Langue and the other in community Concepción de María | There are two (2) local offices for greater permanence in the communities, shorter trips and with greater security, generating more commitment and better communication | Internal |
| Young people in the process of vocational technical training facilitated by INFOP. | 16 young people from the communities of Las Olivas, Isletas Arriba, El Llano, El Aguacatal and La Faja participate in a technical training program in INFOP in computing, electricity, metal structures, tailoring and beauty | Internal. |

- FACTORS THAT LIMIT OR HINDER THE EXECUTION OF THE PROJECT:

What do you consider to have been the internal and external factor(s) that limit or hinder the achievement of the Results and/or Indicators foreseen in the project?

1) Concepción de María, Langue, Valle.

| Identified Element | Limiting influence on the Project | Internal or External Origin? |
| --- | --- | --- |
| Poor condition of bridge boxes on the route to the communities. | There are two bridges in poor condition that represent a risk for the population that travels through the area, generating a problem when the flow of the streams and river increase, not allowing them to cross because the risk is high that one of the infrastructures collapses, you have to wait for the flow to go down to get through | External. |

2) Concepción de María, Choluteca.

| Identified Element | Limiting influence on the Project | Internal or External Origin? |
| --- | --- | --- |
| Insecurity in the area | The security plan was implemented, putting into practice all the protocol to protect the physical integrity of the technical team and avoid unpleasant situations or events to regret. In the last six (6) months, the situation of insecurity has decreased, lowering tensions, and greater tranquility is perceived in the population. | External |

- THE PROJECT MONITORING AND EVALUATION PROCESS:

It is very important to know how the Monitoring and Evaluation activities have contributed to the control, correction and evaluation of the actions of the Project. Please provide the requested information, with special emphasis on the contribution you have made to the proper execution of the project

- Azabache

| Monitoring and Evaluation Activity | Was it made? |  |  | Contribution of the activity to the proper implementation of the Project |
| --- | --- | --- | --- | --- |
|  | YES | NO | Date |  |
| Field visits to carry out the Monitoring Establishing good communication with group leaders | x X x | _ __ | July to December 2023. January to June 2024 July to December 2023 | Direct contact with the members of the groups. Leaders and group members are receptive to the work that V H does Confidence in the work carried out by Vecinos Hondura is increased by the beneficiaries, as well as V H with the beneficiaries. This allows the fulfillment of internal and external commitments by groups and other people. In Azabache Updating of accounting books as part of the administrative accompaniment Motivation to recover previous loans and facilitate access to new financing Signing of new financing agreements Reminder of the loan payment date with the groups of entrepreneurs. Maintain constant communication with part of the members of the groups, in what is the follow-up and monitoring of loans. Verification of population data, confirmation of people who will participate in trainings A monthly consolidated technical report is prepared and presented A telephone directory of people from partner communities and non-members of groups was developed, this facilitates communication with managers and members Communication is maintained by telephone with the directors of organized groups to monitor activities. |
| Identification of internal and external factors influencing project execution | x |  | July to December 2023 | Define intervention strategies and implement safety measures to reduce risks to personnel. Low-cost organizations manage savings accounts to minimize risks VH's leadership in communities. The experience acquired by the beneficiaries in the management of the agreement and loan Availability of a revolving fund to facilitate loans to organized groups. Commitment of organized groups to repay funds in loans. There are capacities in organizations for organizational and administrative functioning. |
| Retrieving Lessons Learned | x |  | Permanent | The commitment shown by organized groups is the key to meeting their obligations to repay loans and advance their economic activities. |

2) Concepción de María, Choluteca

| Monitoring and Evaluation Activity | Was it made? |  |  | Contribution of the activity to the proper implementation of the Project |
| --- | --- | --- | --- | --- |
|  | YES | NO | Date |  |
| Field visits to monitor activities | x |  | July to December 2023. | Socialization of the project with the beneficiary population in the different communities (La Plomosa, La Majada, Las Trojas, El Peñón #1, El Peñón #2, Nueva Unión, Las Mesas and San Isidro) and communities of Concepción de María Langue (Isletas abajo, Isletas arriba, Copetillo, Las Olivas, El Aguacatal, Las Arandas and El Llano). Direct observation, immediate guidance and taking notes so that the volunteers can follow up on specific issues (hygiene, feeding the child, taking advantage of garden products and participation in the project). Motivate, guide and seek solutions to the problems observed. Analyze that the situation of increases is generalized, they must adapt while continuing to advance in the development of the projects. Follow-up visits were made to groups of strategic grain reserves and productive initiatives for organizational strengthening (updating of internal regulations), administrative strengthening in the updating of accounting record books. |
| Identification of internal and external factors that influence the execution of the project. | x |  | July to December 2023. July to December 2023. | Define new intervention strategies and implement safety measures to reduce risks to personnel Complement the project facilitation team with volunteer staff from the area to advance with the execution of activities and enable the sustainability of the project Community volunteering with greater capacities in the accompaniment and performance of strategic activities, generating self-sustainability in the processes developed. Local organizations maintain strategic reserves of grains and seeds, to supply families in times of scarcity based on the implementation of their marketing regulations and maintain the quality of the products. The participation of women is significant in decision-making spaces in the Municipal Council of Guarantee is led by women, in the seven (7) CIAL organized, 49 women participate; Of 12 strategic grain reserves, seven (7) are led by women. Among the alternatives that are promoted are: the diversification of crops, planting of local crops that adapt to the conditions of the area (sweet potatoes, squash, beans, alacin); these in turn, are cover crops and contribute to maintaining humidity, as well as stubble management. Families are also stocking up on corn and beans through strategic grain reserves. Sales of corn and beans are rationed according to the needs of families There is significant involvement and participation of different actors in development processes, mainly women and young members of community organizations, civil society, and municipal authorities. There is high motivation, interest and commitment in the implementation of the project, a sense of belonging and a greater role in the performance of the different activities, which is a determining factor in the training and learning process that translates into the development of capacities of participants in training activities. Evidence of the existing motivation is the organization and experimentation of producers organized in CIAL, articulation of institutions and social organizations in the Municipal Council for the Guarantee of Rights, community organizations articulated in the Association of Communities United for the Defense of their Rights. (ACUDD) The leverage of financing with funds from the Lutheran World Federation and Groundswell International project has been key in achieving the objectives and results sought, which in turn makes it possible to expand the impact of the actions carried out. |
| Technical team meetings to prepare a report | x |  | July to December 2023 | Develop reflection and analysis of the context to have a clearer perspective of our actions in the process of accompaniment to the communities. Consolidate information from the components and enrich learning collectively Necessary and timely information, not only with the execution of the activity, but also with the experiences (from observation, conversation and mention of the participants) from the application of knowledge by the participating volunteers, families and organizations Spaces for analysis of the process, context, progress in contributing to significant changes in communities and the consolidation of information. |

Concepción de María, Langue, Valle.

| Monitoring and Evaluation Activity | Was it made? |  |  | Contribution of the activity to the proper implementation of the Project |
| --- | --- | --- | --- | --- |
|  | YES | NO | Date |  |
| Field visits to socialize the project and carry out the monitoring Establishment of good communication with group leaders | x X X X |  | July to December 2023. January to June July to December 2023. Permanent -January to June Permanent | -Direct contact with the members of the groups. -Leaders and group members are receptive to the work VH does. -Maintain constant communication with members of the groups to carry out future actions -A monthly consolidated technical report is prepared and presented. -A telephone directory of people from partner communities and non-members of groups was developed, this facilitates communication with managers and members In Langue -Community visits to share action plans -Follow-up on the commitments of the participants in the activities to be carried out -Identifying community leadership to coordinate activities -Permanent accompaniment to community organizations to define strategic plans Communication is maintained by telephone with the directors of organized groups to monitor activities -There is good communication with community leadership and participating families -There is a database of resident families and participants in the project -A process of training for community leadership has been initiated to support political, strategic and organizational actions |
| Identification of internal and external factors that influence the execution of the project. | X X |  | July to December 2023 January to June. Permanent | -Define intervention strategies and implement safety measures to reduce risks to personnel. -VH's leadership in communities -Availability of a revolving fund to facilitate loans to organized groups. -There are capacities in organizations for organizational and administrative functioning -Leaders committed with project activities -Institutional coordination with AHJASA, INFOP and Local Government to move forward with the activities .The leadership of the women's network is important for the sustainability of activities -There is willingness and interest of the local government authorities to coordinate efforts for community development |

- UPCOMING ACTIVITIES:

Please explain, how will the learning obtained in the first months of project execution be incorporated during the time remaining to conclude it?

8.1. In Azabache

The decision has been made to close the local office in Azabache and occasional visits to the area will be made next year

- Follow-up by Vecinos Honduras staff to recover credits from producer groups granted in 2023 and facilitate procedures for new credits in 2024

- Groups must decide how much financing they need to develop their productive activities

- It is advisable to continue supporting groups and individuals with the revolving fund

8.2 Concepción de María, Choluteca

Young people are not permanent in the communities and/or groups, follow up on those who remain in the enterprises and support so that the enterprises continue to operate.

Strategic grain reserves continue with their productive activities, their monitoring is key to lead them to organizational and financial sustainability.

The Dry Corridor project financed by Groundswell is an important component to leverage other projects carried out by Vecinos Honduras in the region, in this sense an agreement of understanding has been reached that the monitoring of the work in the area will continue from the accompaniment of ACESH, who will assume the responsibility of continuing with the process that VH achieved in the communities of Concepción de María.  Choluteca, the perspective is that VH will be concentrated in communities in the Concepción de María area, municipality of Langue, department of Valle.

8.3. Concepción de María, Langue.

The project has initiated actions in the area of Concepción de María, Langue, identifying community leadership, socializing the main activities to be carried out during the time of intervention.

Develop a plan aimed at the fulfillment of the activities and results of the project.

In the next semester, progress will be made with most of the planned activities, related to the strengthening of social economy groups and community organizations in financial and organizational aspects.

The project carried out the activities with the involvement of several key actors who have contributed to generate a positive attitude changes in the members of the organizations. The coordination with AHJASA, INFOP, ACESH and Local Government has facilitated progress in the development of operational and strategic actions to carry out the activities

Working together with staff from other VH projects (HEKS/EPER, MISEREOR and Groundswell International) allows for greater coordination in the activities of all projects and this has a positive impact on the participants because they strengthen their capacities and at the institutional level they maximize results

The participating families in Concepción de María, Langue have an organizational and productive basement, they are organized in circles, networks, Water Administrative Boards, patronatos and other community organizations and many families have traditional crops (corn, beans, bananas, cassava, fruit trees and medicinal plants)

PHOTO GALLERY:

Please send the photographs of the project, in a separate file from this report